## ExecutioveSummary (hidden)
Batch | Identified Batch jobs | Dry Run | Request | Response |  | Expected (NFR) | Actual
IDT | 185
BIF-In and BIF-Out Feeds | 85
CRM | 2
Record Keeping (MI Extract) | 31
Config Reporting | 15
Consumer Layer Perf Testing Readiness | Total Scripts | Design Ready | Data Ready | Scripts Ready for execution | Executed | Performance Defects/ Defects | Data / Parameter Ready
CRM | 30 | 1 | 40% | 12
WFI | 8 | 1 | 62.5% | 5
Participant Portal | 19 | 1 | 5.263% | 1
Advisor Portal | 26 | 1 | 23.08% | 6
Sponsor TPA Portal | 16 | 1 | 50% | 8
Financial Reports ( Reports) | 10 | 1 | 0%
IDT ( Reports) | 7 | 1 | 0%
SID ( Reports) | 10 | 1 | 0%
Self Service ( Reports) | 10 | 1 | 0%
Eforms ( Config Reporting) | 10 | 1 | 0%

## PerformanceTesting Summary
|  |  | Build Phase |  |  |  | Execution Phase
Total Scripts In-Scope | In-Progress (UAT) | Completed (UAT) | Blocked (CERT) | Completed (CERT) | No of Cycles Executed (UAT) | Defects Logged (UAT) | No of Cycles Executed (CERT) | Defects Logged (CERT)
137 | 47 | 90 | 105 | 32 | 60 | 35 | 0 | 2
Percentage | 34.31% | 65.69% | 76.64% | 23.36%

## Performance Testing
|  | Build Phase |  |  |  |  | Execution Phase |  |  |  | Remarks
Program | Project | Flows In-Scope | In-Progress (UAT) | Completed (UAT) | In-Progress (CERT) | Completed (CERT) | No of Cycles in UAT | No of Cycles (CERT) | Defects Logged (UAT) | Defects Logged (UAT)
CC Sales CRM WFI | TRUCKING | 30 | 9 | 21 | 9 | 12 | 4
| SC | 8 | 0 | 8 | 0 | 5 | 8
Portals | AVIATION | 19 | 7 | 12 | 7 | 1 | 5
| SHS | 17 | 2 | 15 | 2 | 6 | 1
| WC | 16 | 3 | 13 | 3 | 8 | 4
OBIEE Reports | BU6 | 10 | 10 | 0 | 10 | 0
| BU7 | 7 | 0 | 7 | 0 | 0
| BU8 | 10 | 9 | 1 | 9 | 0
| BU9 | 10 | 7 | 3 | 7 | 0
| BATCHES | 2
| PUBSUB | 31
1
TOTAL |  | 127 | 47 | 80 | 47 | 32 | 60 | 0 | 35 | 2
Note on H6: MassMutual Financial Group: 1 test Along with advisor and Sponsor scenario and 3 tests along with sponsor in Qa

## Issue log (hidden)
Date: | Issue description
2014-03-04 | Portal is down since 3/3,No Access in CRM PP Alis Mashup screen,OBIEE main functionalities are not accissible from our end, DMOS ticket has bee raised to access OBIEE but it is still in-progress status
2014-03-04 | While retesting The CRM Defects which were in “Re-test” status, we observed that the CRM Dev application is not working properly as the ALIS mashup pages were not coming up(Getting hanged in the same page-screenshot attached ). So, we could not proceed with retesting and closing the CRM Defects.
2014-03-07 | OBIEE main functionalities are not accissible from our end, DMOS ticket has bee raised to access OBIEE but it is still in-progress status;hence couldnot proceed with SID and Financial reports. Faced intermitten issues in sponsor and advisor portal; No Access in CRM PP Alis Mashup screen;we observed that the CRM Dev application is not working properly as the ALIS mashup pages were not coming up(Getting hanged in the same page-screenshot attached ). So, we could not proceed with retesting and closing the CRM Defects.
2014-03-08 | Intermittent issue found in Sponsor portal,OBIEE main functionalities are not accissible from our end, DMOS ticket has bee raised to access OBIEE but it is still in-progress status;hence couldnot proceed with SID and Financial reports. Faced intermitten issues in sponsor and advisor portal; No Access in CRM PP Alis Mashup screen;we observed that the CRM Dev application is not working properly as the ALIS mashup pages were not coming up(Getting hanged in the same page-screenshot attached ). So, we could not proceed with retesting and closing the CRM Defects.
2014-03-09 | No Access in CRM PP Alis Mashup screen;we observed that the CRM Dev application is not working properly as the ALIS mashup pages were not coming up(Getting hanged in the same page-screenshot attached ). So, we could not proceed with retesting and closing the CRM Defects.
2014-03-10 | No Access in CRM PP Alis Mashup screen, hence could not proceed with CRM scripting
2014-03-11 | No Access in CRM PP Alis Mashup screen, hence could not proceed with CRM scripting; Few sponsor portal Alis mashup pages are coming blank; Most of the SID scenarios are not available in the application, need further clarification on it.
2014-03-14 | Waiting for the SID and Financial report navigation flows from portal. Slowness and Intermittent issues are observed in sponsor and advisor portal throughout the day, also few testIDs were not working properly.When we are clicking on Eligibility status or other options under Everything else of participant management we are getting 502 proxy error, hence could not proceed with the rest of the sponsor scripts. We also noticed “View Alis” Link is missing in advisor portal QA for few login IDs . Few others have view alis link but they don’t have pre-defined report option and only we found one ID TSSITAdv143 which has both view alis link and pre-defined report option but if we click on a particular report link like Highly Concentrated Participant Portfolio Report then it is throwing 500 error and to re-check it when we clicked on back to all report link then we could not see that particular report link in the list anymore. Now when we are trying to login with the same ID TSSITAdv143 it is asking for password change. Hence could not proceed with rest of the self service reports.
2014-03-15 | Waiting for the SID and Financial report navigation flows from portal. No Access in CRM PP Alis Mashup screen, hence could not proceed with CRM scripting
2014-03-16 | Waiting for the SID and Financial report navigation flows from portal. No Access in CRM PP Alis Mashup screen, hence could not proceed with CRM scripting
2014-03-17 | Waiting for the SID and Financial report navigation flows from portal. No Access in CRM PP Alis Mashup screen, hence could not proceed with CRM scripting. In sponsor portal error page is coming up after continue button click
2014-03-18 | Could not close performance defect in QC as response times are high and in Alis mash up page unable to save address and contact details in DEV.Waiting for the SID and Financial report navigation flows from portal. No Access in CRM PP Alis Mashup screen, hence could not proceed with CRM scripting.
2014-03-21 | Today we checked the PP environment but it is still not up for portal and in CRM PP Alis mashup pages are not accessible. Fund to Fund (From Participant Portal): Login with valid user id -> Dashboard ->Manage investments ->Move Money between Investments ->continue with balance transfers-> When we tried to transfer balance from source to destination account we got an error page Loan Initiation (From Participant Portal): User Login with valid credentials ->My Account ->Taking Money Out ->Model and Request a Loan (Server Error Page) Withdrawal (From Sponsor Portal) : User login with valid credentials -> Adopter Dashboard Page -> Account Dashboard--> Select “Participant Management” Menu - > Taking Money Out -> Initiate withdrawal-> Fill up details and click next-> Fill up mandatory fields and click next-> At arrangement ID lookup- getting error message (you don’t have access rights to this screen)
2014-03-22 | We are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. We tried to navigate the withdrawal scenario in QA using the new test ID but that also didn’t work properly for this scenario. Today again tried to navigate the fund to fund and loan initiation flow in Participant QA but observed same issue.
2014-03-24 | We are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. However, today we again tried to check Loan initiation scenario in Participant portal QA and we are getting a new issue there.
2014-03-25 | As data migration is going on, we are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. Yet to get any response for Loan initiation, Fund to fund from Rama and Gopi responded that there is an open defect for withdrawal.
2014-03-28 | 1) Not enough balance to initiate a loan (Checked with few existing test IDs); please see the attached screenshot. 2) Unable to do fund to fund transfer; multiple error page cropped up. Steps to re-produced the error: Fund to Fund (From Participant Portal): Login with valid user id -> Dashboard ->Manage investments ->Move Money between Investments ->continue with balance transfers->Transfer balance by clicking next-> Submit button click->Error page (Please find the attached screen shots of the same). Then again followed the same process and tried to transfer from another fund to a different fund but found “Something went wrong. Please try again later” message on the top of that page. (Screen shot attached) Seeing this issue we opened a fresh session and tried this activity there but when we clicked on continue with balance transfer button it showed those pending transactions and we could not proceed further (screen shot attached). Moreover, when we clicked on the cancel link it took us to some other page where we again clicked on cancel link to cancel this pending fund transfer activity but instead of canceling that transaction it moved to the historical activity page.] 3) For withdrawal there is an open defect in QC; defect ID 14368. 4) Could not see any new OBIEE reports of new report category in QA and DEV IDs are not working currently. 5) CRM PP Alis mashup pages are still not coming up. Hence we though to capture traffic for DEV, as in dev most of the tabs and options are working. But from my ID while recording I’m getting high interactivity issue and for Ajoy he does not have write access to some of the pages
2014-03-29 | As data migration is going on, we are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. We didn't perform any scripting activity in Portal scale down env. as it may impact BIF.
2014-03-30 | As data migration is going on, we are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. We didn't perform any scripting activity in Portal scale down env. as it may impact BIF.
2014-03-31 | As data migration is going on, we are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. Also we could not start withdrawal in lower env. as an open defect exists. Old QA Participant IDs are not working.
2014-04-01 | As data migration is going on, we are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. Also we could not start withdrawal in lower env. as an open defect exists. Old QA Participant IDs are not working.
2014-04-05 | As data migration is going on, we are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. Old QA Participant IDs are not working.
2014-04-07 | As data migration is going on, we are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. Old QA Participant IDs are not working.
2014-04-08 | As data migration is going on, we are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. Old QA Participant,Sponsor and Advisor IDs are not working.
2014-04-11 | As data migration is going on, we are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. Old QA Participant, Advisor IDs are not working.
2014-04-12 | As data migration is going on, we are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. Old QA Participant, Sponsor, Advisor IDs are not working hence we could not check pending scenarios as well as OBIEE reports from portal end. Charu confirmed that most of the sponsor IDs are locked their team is working with their own ID, which cann't be shared. Also we are getting high interactivity issue in CRM lower env. hence unable to record anything new.
2014-04-13 | New PP IDs are not working for sponsor, Advisor and Participant portal, CRM PP has same issue, Imp links and tabs are not coming up.
2014-04-15 | None of the portal PP IDs are working,CRM PP has same issue, Imp links and tabs are not coming up for Madhu and For Ajoy high interactivity issue got resolved just now. Noticed Intermittent issue for Alis mashup pages ,Under Account setup tab we are not seeing any template name in the list
2014-04-19 | Participant Dashboard is not accessible from Sponsor and Advisor portal also Save as Draft button in Advisor is throwing server error. Yet to get the latest Participant portal in PP; Also for Disbursement History and View Payroll File we are getting error page in sponsor.
2014-04-20 | Participant Dashboard is not accessible from Sponsor and Advisor portal also Save as Draft button in Advisor is throwing server error.Yet to get the latest Participant portal in PP. For someof the CRM scenario we need proper user role.
2014-04-21 | Participant Dashboard is not accessible from Sponsor and Advisor portal also Save as Draft button in Advisor is throwing server error.Yet to get the latest Participant portal in PP, however while checking the workaround we observed various issue in Participant portal-like go to tool, contact us,model a loan, change investment selection throwing error and processrolin and loan payoff are not present. We have been informed from onsite not to use CRM until further notice. ALis screen is not comingup in WFI.
2014-04-22 | Participant Dashboard is not accessible from Sponsor and Advisor portal also Save as Draft button in Advisor is throwing server error.Yet to get the latest Participant portal in PP, however while checking the workaround we observed various issue in Participant portal-like go to tool, contact us,model a loan, change investment selection throwing error and processrolin and loan payoff are not present, also eForms are not working as expected. We have been informed from onsite not to use CRM until further notice. Server error is at Alis mashup screen for WFI.
2014-04-26 | Participant Dashboard is not accessible from Sponsor and Advisor portal also Save as Draft button in Advisor is throwing server error.Yet to get the latest Participant portal in PP.We have been informed from onsite not to use CRM until further notice.
2014-04-27 | After login in error page is coming up for sponsor portal and in Advisor View Alis link is missing. Yet to get the latest Participant portal in PP.We have been informed from onsite not to use CRM until further notice.
2014-04-28 | In participant portal we are getting error page after login for all the PP test users. We have been informed from onsite not to use CRM until further notice. Participant Dashboard is not accessible from Sponsor and Advisor portal also Save as Draft button in Advisor is throwing server error.Yet to get the latest Participant portal in PP, however while checking the workaround we observed various issue in Participant portal-like go to tool, contact us,model a loan, change investment selection throwing error and processrolin and loan payoff are not present, also eForms are not working as expected.
2014-04-29 | defects exist in QA for withdrawal and loan initiation, We have been informed from onsite not to use CRM until further notice
2014-05-02 | No Create message/Edit Message/Delete/View Message Button present for advisor portal in QA.
2014-05-03 | No Create message/Edit Message/Delete/View Message Button present for advisor portal in QA. However, today we have been informed that these are shifted to Day1 +
2014-05-04 | defects exist in QA for withdrawal and loan initiation
2014-05-05 | Today we faced issues at Loan initiation in QA Participant portal with different user IDs.
2014-05-11 | Issue persists in Participant portal in QA for Loan initiation. Participant and Sponsor PP are not accessible as after continue button click noticed error. In PP advisor portal View Alis link is missing.
2014-05-12 | eForm links are not working and error messages are coming for every self-service report.
2014-05-13 | 1) I got error message at participant dashboard for advisor portal in PP. (Flow: Launch->Login->My account->View Alis-> Search with participant last name ->Click on the 1st account number to got to the participant management dashboard). 2) Again while validating the above flow I got site is experiencing error page after view Alis link click and before that I checked with another user and there I got error page after participant search in Advisor portal PP. Test IDs:CGahan36231 and CLombardi31678 were used 3) Also, I got the similar kind of issue in PP sponsor portal for participant search 4) Found Third party server not responding error after PP participant portal login.
2014-05-16 | Sponsor and Participant portal PP has issue after login, Advisor PP has issue at participant search. In Participant Portal Loan initiation has issue.
2014-05-17 | 1) Delete bank button is not working in Participant portal in QA. Contacted offshore PoC for the same and they logged defect against it. Defect number : 15788 2) Today Also same issue persists in participant portal applications, getting error page just after login. 3) In Sponsor portal at participant search got error page and for advisor portal at search participant when I searched with ”%a” then also it asked for search key.

## TS Code Drop (hidden)
Week Ending |  | 2015-01-01 | 2015-01-08 | 2015-01-15 | 2015-01-22 | 2015-01-29 | 2015-02-05 | 2015-02-12 | 2015-02-19 | 2015-02-26 | 2016-03-04 | 2016-03-11 | 2016-03-18 | 2016-03-25 | 2016-04-01 | 2016-04-08 | 2016-04-15 | 2016-04-22 | 2016-04-29 | 2016-05-06 | 2016-05-13
ALIS Standalone |  | V13.002a | 13.002b | 13.003 | V13.003 | V13.003a | V13.003a | 13.003a | V13.004 | V13.004 | 13.004 | 13.004 | 13.005 | 13.005 | 13.005 | 13.005 | 13.006 | 13.006 | 13.006 | 13.006 | 13.006
BIF Dev (Dev 2) | ALIS | 13.002a | V13.002b | V13.002b | 13.003 | 13.003a | 13.003a | 13.003a | 13.003a | 13.004 | 13.004 | 13.004 | 13.004 | 13.005 | 13.005 | 13.005 | 13.005 | 13.006 | 13.006 | 13.006 | 13.006
| BIF | R5 | R5 | R5 | R6 | R6 | R6 | R6 | R6 | R7 | R7 | R7 | R7 | R8 | R8 | R8 | R8 | R9 | R9 | R9 | R9
IUT (Dev 3) | ALIS | V13.X | V13.002b | V13.002b | 13.002b | 13.003 | 13.003a | 13.003a | 13.003a | 13.004 | 13.004 | 13.004 | 13.004 | 13.005 | 13.005 | 13.005 | 13.005 | 13.006 | 13.006 | 13.006 | 13.006
| BIF | R5 | R5 | R5 | R5 | R6 | R6 | R6 | R6 | R7 | R7 | R7 | R7 | R8 | R8 | R8 | R8 | R9 | R9 | R9 | R9
| SIL | R5 | R5 | R5 | R5 | R6 | R6 | R6 | R6 | R7 | R7 | R7 | R7 | R8 | R8 | R8 | R8 | R9 | R9 | R9 | R9
| CRM | R5 | R5 | R5 | R5 | R6 | R6 | R6 | R6 | R7 | R7 | R7 | R7 | R8 | R8 | R8 | R8 | R9 | R9 | R9 | R9
| Consumers | R5 | R5 | R5 | R4 | R6 | R6 | R6 | R6 | R7 | R7 | R7 | R7 | R8 | R8 | R8 | R8 | R9 | R9 | R9 | R9
SIT (ST2) | ALIS | 13.002a | 13.002a | V13.002b | V13.002b | V13.003 | 13.003a | 13.003a | 13.003a | 13.003a | 13.004 | 13.004 | 13.004 | 13.004 | 13.005 | 13.005 | 13.005 | 13.005 | 13.006 | 13.006 | 13.006
| BIF | R4 | R4 | R5 | R5 | R5 | R6 | R6 | R6 | R6 | R7 | R7 | R7 | R7 | R8 | R8 | R8 | R8 | R9 | R9 | R9
| SIL | R4 | R4 | R5 | R5 | R5 | R6 | R6 | R6 | R6 | R7 | R7 | R7 | R7 | R8 | R8 | R8 | R8 | R9 | R9 | R9
| Consumers | R4 | R4 | R5 | R5 | R5 | R6 | R6 | R6 | R6 | R7 | R7 | R7 | R7 | R8 | R8 | R8 | R8 | R9 | R9 | R9
E2E/UAT | ALIS | 13.001a | 13.001a | 13.001a | 13.002b | 13.002b | 13.002b | 13.003a | 13.003a | 13.003a | 13.003a | 13.004 | 13.004 | 13.004 | 13.004 | 13.005 | 13.005 | 13.005 | 13.005 | 13.006 | 13.006
| BIF | R4 | R4 | R4 | R5 | R5 | R5 | R6 | R6 | R6 | R6 | R7 | R7 | R7 | R7 | R8 | R8 | R8 | R8 | R9 | R9
| SIL | R4 | R4 | R4 | R5 | R5 | R5 | R6 | R6 | R6 | R6 | R7 | R7 | R7 | R7 | R8 | R8 | R8 | R8 | R9 | R9
| Consumers | R4/R5 | R4/R5 | R4 | R5 | R5 | R5 | R6 | R6 | R6 | R6 | R7 | R7 | R7 | R7 | R8 | R8 | R8 | R8 | R9 | R9

## Sheet2 (hidden)
RS TS Performance Testing Efforts
ALIS R1
Design Phase: ALIS Round1:v11
Build Phase
Execution Phase
Reporting Phase
ALIS R2
Design Phase: ALIS Round2:v12
Build Phase
Execution Phase
Final Reporting Phase
ALIS R3
Design Phase: ALIS Round3:v12
Build Phase
Execution Phase
Final Reporting Phase
IDT Day1
Design Phase: IDT
Build Phase: Only IDT /OBIEE (Canned Reports)
FMT Migration
Design Phase: FMT MIGRATION
Build Phase
Execution Phase
Final Reporting Phase
WFI
Design Phase: WFI
Build Phase
Execution Phase
CRM -Phase1 (Only ALIS Impacted areas)
Design Phase: CRM
Build Phase
Execution Phase
CRM -Phase2
Design Phase: CRM
Build Phase
Execution Phase
OBIEE Reporting
Design Phase: FMT MIGRATION
Build Phase
Execution Phase
Final Reporting Phase
PORTAL-TPA/SP
Design Phase: PPT PORTAL
Build Phase (Resource A)
Execution Phase
PORTAL-ADV
Design Phase: PPT PORTAL
Build Phase (Resource B)
Execution Phase
PORTAL-PPT
Design Phase: PPT PORTAL
Build Phase (Resource B)
Execution Phase
Full Portal +WFI+CRM+OBIEE Test (A)
Consolidated Build Phase in Preprod Environment
Execution Phase(Portal After Release3)
Final Reporting Phase
Full RS Batch Processes Test (B)
Design Phase: RS Batch Processes
Build Phase in Preprod Environment
Execution Phase
Final Reporting Phase
(A )+ (B) End 2 End Performance Test
Design Phase:
Execution Phase
Final Reporting Phase
Performance TRIAGE Tuning Projects
Design Phase:
Build Phase in Prod Environment
Execution Phase
Final Reporting Phase