## MAJESCO WORK Estimates_Summary
ACTIVE PROJECTS
Trucking | Percentage Completed | Status | Planned Start Date | Planned End Date | Revised Start Date | Revised End Date | COMMENTS
|  |  | 2014-10-19 | 11/25/2014 12/10/2014
Design Phase: |  |  | 2014-10-19 | 2014-10-30 |  |  | MJSCO(100%)
Architectural Overview | 100% |  | 2014-10-19 | 2014-10-23
Demo, Access and Setup by Project/QA Team | 100% |  | 2014-10-19 | 2014-10-23
Identify Inscope/out of Scope Transactions | 100% |  | 2014-10-19 | 2014-10-23
Identify the Performance Flows for Script Development | 100% |  | 2014-10-19 | 2014-10-23
Design Test Scenarios | 100% |  | 2014-10-19 | 2014-10-30 |  | 2014-10-30 | MJSCO
Enviornment,Monitoring requirements (Pre-Prod/PROD) | 100% |  | 2014-10-19 | 2014-10-23
Performance Test Data Requirements | 100% |  | 2014-10-19 | 2014-10-23
Prepare, Publish, Review and Sign-OFF Performance Test Plan | 100% |  | 2014-10-19 | 2014-10-23
Build Phase | 10% |  | 10/26/2014 11/9/2014 11/30/2014 12/15/2014 | 10/30/2014 11/13/2014 12/18/2014 | 2014-12-15 | 2014-12-18
Test Environment Delivery | 0%
Data Preperation
Develop/Modify Performance Test Scripts
Monitoring setup
LOAD MODEL
Scenarios development and Review
Execution Phase | 0% |  | 11/2/2014 11/16/2014 12/21/2014 | 11/20/2014 12/7/2014 01/15/2014 | 2014-12-21 | 2014-01-15
Profiled Performance Test Execution, Analysis, Remediation
Stress Test Execution, Analysis, Remediation
Duration Test Execution, Analysis, Remediation
Reporting Phase | 0% |  | 11/23/2014 01/18/2014 | 11/25/2014 01/20/2014 | 2014-01-18 | 2014-01-20
Prepare Final Test Results
Review the Test Results
Note on B4: MassMutual Financial Group: Performance Team to get hands on droppin the Loan,contribution files. 1. Contribution 2. DemoGraphics 3. Compensation 11/13/2015 -we cannot run any batch files in preprod/prod as it impacts goldcopy before migrated to Prod. 11/18/2015: round1 deck ready ot execute. Round 3 new stuff need to validate in new envt. Having issues with Pc12. some scripts not executing.
Note on B15: MassMutual Financial Group: 12/2/2015 -Env. Delivery ecpected on Dec14

## Milestones_GantChart
Projects | May |  | June | July |  | Aug |  | Sept |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  | Jan |  |  | Feb |  | Mar |  |  | Apr |  | May | June | July | Aug
LOB | 28 |  | ALIS R1 | 10
LOB | [5 empty] | 19 | ALISR2 |  | 11
LOB | [14 empty] | 19 ALISR3 | 30 |  | 9 | ALISR3 |  |  |  | ALISR3 | 20 |  | 15
LOB | [6 empty] | 14 |  |  |  | IDT |  | 5 IDT OBIEE | 16
LOB | [5 empty] | 19 | PPT Portal |  | 11 | [12 empty] | 16 |  |  |  | 1 | 28
LOB | [7 empty] | 1 |  | PORTAL TPA/SP |  | 25 | [9 empty] | 16 |  |  |  | 1 | 28
LOB | [24 empty] | 18 |  |  | 4
LOB | [12 empty] | 1 |  |  |  | WFI | [8 empty] | 1 | 29
LOB | [13 empty] | 19 | CRM PH1 | [10 empty] | 1 | 29
LOB | [19 empty] | 23 |  |  |  |  | 30 | 1 | 29
LOB |  |  |  |  | 20 |  |  |  | FMT Migration | [15 empty] | 30 | 1 | Phase2 29
LOB | [20 empty] | 1 |  |  |  | 26 |  | 29
LOB | [25 empty] | 1 | 29
LOB | [25 empty] | 1 | 29
LOB | [26 empty] | 15 (A) | 10
LOB | [16 empty] | 2 | [6 empty] | Batch Sequencing (B) | [5 empty] | 31
LOB | [27 empty] | 1 | A+B |  |  | 15
LOB | [5 empty] | 1 | [6 empty] | Performance Review Triage Defects Tuning Projects
Complete
In Progress
Not Completed/Planned
Deffered

## ISSUE_lOG
Date: | Issue description
2014-03-04 | Portal is down since 3/3,No Access in CRM PP Alis Mashup screen,OBIEE main functionalities are not accissible from our end, DMOS ticket has bee raised to access OBIEE but it is still in-progress status
2014-03-04 | While retesting The CRM Defects which were in “Re-test” status, we observed that the CRM Dev application is not working properly as the ALIS mashup pages were not coming up(Getting hanged in the same page-screenshot attached ). So, we could not proceed with retesting and closing the CRM Defects.
2014-03-07 | OBIEE main functionalities are not accissible from our end, DMOS ticket has bee raised to access OBIEE but it is still in-progress status;hence couldnot proceed with SID and Financial reports. Faced intermitten issues in sponsor and advisor portal; No Access in CRM PP Alis Mashup screen;we observed that the CRM Dev application is not working properly as the ALIS mashup pages were not coming up(Getting hanged in the same page-screenshot attached ). So, we could not proceed with retesting and closing the CRM Defects.
2014-03-08 | Intermittent issue found in Sponsor portal,OBIEE main functionalities are not accissible from our end, DMOS ticket has bee raised to access OBIEE but it is still in-progress status;hence couldnot proceed with SID and Financial reports. Faced intermitten issues in sponsor and advisor portal; No Access in CRM PP Alis Mashup screen;we observed that the CRM Dev application is not working properly as the ALIS mashup pages were not coming up(Getting hanged in the same page-screenshot attached ). So, we could not proceed with retesting and closing the CRM Defects.
2014-03-09 | No Access in CRM PP Alis Mashup screen;we observed that the CRM Dev application is not working properly as the ALIS mashup pages were not coming up(Getting hanged in the same page-screenshot attached ). So, we could not proceed with retesting and closing the CRM Defects.
2014-03-10 | No Access in CRM PP Alis Mashup screen, hence could not proceed with CRM scripting
2014-03-11 | No Access in CRM PP Alis Mashup screen, hence could not proceed with CRM scripting; Few sponsor portal Alis mashup pages are coming blank; Most of the SID scenarios are not available in the application, need further clarification on it.
2014-03-14 | Waiting for the SID and Financial report navigation flows from portal. Slowness and Intermittent issues are observed in sponsor and advisor portal throughout the day, also few testIDs were not working properly.When we are clicking on Eligibility status or other options under Everything else of participant management we are getting 502 proxy error, hence could not proceed with the rest of the sponsor scripts. We also noticed “View Alis” Link is missing in advisor portal QA for few login IDs . Few others have view alis link but they don’t have pre-defined report option and only we found one ID TSSITAdv143 which has both view alis link and pre-defined report option but if we click on a particular report link like Highly Concentrated Participant Portfolio Report then it is throwing 500 error and to re-check it when we clicked on back to all report link then we could not see that particular report link in the list anymore. Now when we are trying to login with the same ID TSSITAdv143 it is asking for password change. Hence could not proceed with rest of the self service reports.
2014-03-15 | Waiting for the SID and Financial report navigation flows from portal. No Access in CRM PP Alis Mashup screen, hence could not proceed with CRM scripting
2014-03-16 | Waiting for the SID and Financial report navigation flows from portal. No Access in CRM PP Alis Mashup screen, hence could not proceed with CRM scripting
2014-03-17 | Waiting for the SID and Financial report navigation flows from portal. No Access in CRM PP Alis Mashup screen, hence could not proceed with CRM scripting. In sponsor portal error page is coming up after continue button click
2014-03-18 | Could not close performance defect in QC as response times are high and in Alis mash up page unable to save address and contact details in DEV.Waiting for the SID and Financial report navigation flows from portal. No Access in CRM PP Alis Mashup screen, hence could not proceed with CRM scripting.
2014-03-21 | Today we checked the PP environment but it is still not up for portal and in CRM PP Alis mashup pages are not accessible. Fund to Fund (From Participant Portal): Login with valid user id -> Dashboard ->Manage investments ->Move Money between Investments ->continue with balance transfers-> When we tried to transfer balance from source to destination account we got an error page Loan Initiation (From Participant Portal): User Login with valid credentials ->My Account ->Taking Money Out ->Model and Request a Loan (Server Error Page) Withdrawal (From Sponsor Portal) : User login with valid credentials -> Adopter Dashboard Page -> Account Dashboard--> Select “Participant Management” Menu - > Taking Money Out -> Initiate withdrawal-> Fill up details and click next-> Fill up mandatory fields and click next-> At arrangement ID lookup- getting error message (you don’t have access rights to this screen)
2014-03-22 | We are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. We tried to navigate the withdrawal scenario in QA using the new test ID but that also didn’t work properly for this scenario. Today again tried to navigate the fund to fund and loan initiation flow in Participant QA but observed same issue.
2014-03-24 | We are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. However, today we again tried to check Loan initiation scenario in Participant portal QA and we are getting a new issue there.
2014-03-25 | As data migration is going on, we are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. Yet to get any response for Loan initiation, Fund to fund from Rama and Gopi responded that there is an open defect for withdrawal.
2014-03-28 | 1) Not enough balance to initiate a loan (Checked with few existing test IDs); please see the attached screenshot. 2) Unable to do fund to fund transfer; multiple error page cropped up. Steps to re-produced the error: Fund to Fund (From Participant Portal): Login with valid user id -> Dashboard ->Manage investments ->Move Money between Investments ->continue with balance transfers->Transfer balance by clicking next-> Submit button click->Error page (Please find the attached screen shots of the same). Then again followed the same process and tried to transfer from another fund to a different fund but found “Something went wrong. Please try again later” message on the top of that page. (Screen shot attached) Seeing this issue we opened a fresh session and tried this activity there but when we clicked on continue with balance transfer button it showed those pending transactions and we could not proceed further (screen shot attached). Moreover, when we clicked on the cancel link it took us to some other page where we again clicked on cancel link to cancel this pending fund transfer activity but instead of canceling that transaction it moved to the historical activity page.] 3) For withdrawal there is an open defect in QC; defect ID 14368. 4) Could not see any new OBIEE reports of new report category in QA and DEV IDs are not working currently. 5) CRM PP Alis mashup pages are still not coming up. Hence we though to capture traffic for DEV, as in dev most of the tabs and options are working. But from my ID while recording I’m getting high interactivity issue and for Ajoy he does not have write access to some of the pages
2014-03-29 | As data migration is going on, we are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. We didn't perform any scripting activity in Portal scale down env. as it may impact BIF.
2014-03-30 | As data migration is going on, we are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. We didn't perform any scripting activity in Portal scale down env. as it may impact BIF.
2014-03-31 | As data migration is going on, we are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. Also we could not start withdrawal in lower env. as an open defect exists. Old QA Participant IDs are not working.
2014-04-01 | As data migration is going on, we are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. Also we could not start withdrawal in lower env. as an open defect exists. Old QA Participant IDs are not working.
2014-04-05 | As data migration is going on, we are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. Old QA Participant IDs are not working.
2014-04-07 | As data migration is going on, we are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. Old QA Participant IDs are not working.
2014-04-08 | As data migration is going on, we are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. Old QA Participant,Sponsor and Advisor IDs are not working.
2014-04-11 | As data migration is going on, we are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. Old QA Participant, Advisor IDs are not working.
2014-04-12 | As data migration is going on, we are waiting to get the valid test data to start script tweaking activity in pre-prod for portals. Old QA Participant, Sponsor, Advisor IDs are not working hence we could not check pending scenarios as well as OBIEE reports from portal end. Charu confirmed that most of the sponsor IDs are locked their team is working with their own ID, which cann't be shared. Also we are getting high interactivity issue in CRM lower env. hence unable to record anything new.
2014-04-13 | New PP IDs are not working for sponsor, Advisor and Participant portal, CRM PP has same issue, Imp links and tabs are not coming up.
2014-04-15 | None of the portal PP IDs are working,CRM PP has same issue, Imp links and tabs are not coming up for Madhu and For Ajoy high interactivity issue got resolved just now. Noticed Intermittent issue for Alis mashup pages ,Under Account setup tab we are not seeing any template name in the list
2014-04-19 | Participant Dashboard is not accessible from Sponsor and Advisor portal also Save as Draft button in Advisor is throwing server error. Yet to get the latest Participant portal in PP; Also for Disbursement History and View Payroll File we are getting error page in sponsor.
2014-04-20 | Participant Dashboard is not accessible from Sponsor and Advisor portal also Save as Draft button in Advisor is throwing server error.Yet to get the latest Participant portal in PP. For someof the CRM scenario we need proper user role.
2014-04-21 | Participant Dashboard is not accessible from Sponsor and Advisor portal also Save as Draft button in Advisor is throwing server error.Yet to get the latest Participant portal in PP, however while checking the workaround we observed various issue in Participant portal-like go to tool, contact us,model a loan, change investment selection throwing error and processrolin and loan payoff are not present. We have been informed from onsite not to use CRM until further notice. ALis screen is not comingup in WFI.
2014-04-22 | Participant Dashboard is not accessible from Sponsor and Advisor portal also Save as Draft button in Advisor is throwing server error.Yet to get the latest Participant portal in PP, however while checking the workaround we observed various issue in Participant portal-like go to tool, contact us,model a loan, change investment selection throwing error and processrolin and loan payoff are not present, also eForms are not working as expected. We have been informed from onsite not to use CRM until further notice. Server error is at Alis mashup screen for WFI.
2014-04-26 | Participant Dashboard is not accessible from Sponsor and Advisor portal also Save as Draft button in Advisor is throwing server error.Yet to get the latest Participant portal in PP.We have been informed from onsite not to use CRM until further notice.
2014-04-27 | After login in error page is coming up for sponsor portal and in Advisor View Alis link is missing. Yet to get the latest Participant portal in PP.We have been informed from onsite not to use CRM until further notice.
2014-04-28 | In participant portal we are getting error page after login for all the PP test users. We have been informed from onsite not to use CRM until further notice. Participant Dashboard is not accessible from Sponsor and Advisor portal also Save as Draft button in Advisor is throwing server error.Yet to get the latest Participant portal in PP, however while checking the workaround we observed various issue in Participant portal-like go to tool, contact us,model a loan, change investment selection throwing error and processrolin and loan payoff are not present, also eForms are not working as expected.
2014-04-29 | defects exist in QA for withdrawal and loan initiation, We have been informed from onsite not to use CRM until further notice
2014-05-02 | No Create message/Edit Message/Delete/View Message Button present for advisor portal in QA.
2014-05-03 | No Create message/Edit Message/Delete/View Message Button present for advisor portal in QA. However, today we have been informed that these are shifted to Day1 +
2014-05-04 | defects exist in QA for withdrawal and loan initiation
2014-05-05 | Today we faced issues at Loan initiation in QA Participant portal with different user IDs.
2014-05-11 | Issue persists in Participant portal in QA for Loan initiation. Participant and Sponsor PP are not accessible as after continue button click noticed error. In PP advisor portal View Alis link is missing.
2014-05-12 | eForm links are not working and error messages are coming for every self-service report.
2014-05-13 | 1) I got error message at participant dashboard for advisor portal in PP. (Flow: Launch->Login->My account->View Alis-> Search with participant last name ->Click on the 1st account number to got to the participant management dashboard). 2) Again while validating the above flow I got site is experiencing error page after view Alis link click and before that I checked with another user and there I got error page after participant search in Advisor portal PP. Test IDs:CGahan36231 and CLombardi31678 were used 3) Also, I got the similar kind of issue in PP sponsor portal for participant search 4) Found Third party server not responding error after PP participant portal login.
2014-05-16 | Sponsor and Participant portal PP has issue after login, Advisor PP has issue at participant search. In Participant Portal Loan initiation has issue.
2014-05-17 | 1) Delete bank button is not working in Participant portal in QA. Contacted offshore PoC for the same and they logged defect against it. Defect number : 15788 2) Today Also same issue persists in participant portal applications, getting error page just after login. 3) In Sponsor portal at participant search got error page and for advisor portal at search participant when I searched with ”%a” then also it asked for search key.

## ISSUE LOG
project1
Phase | Date | Comments
Develop/Modify Performance Test Scripts
| 2015-06-23 | Modified the "MJSCO_Menu1" script (resripted) and completed the data validation
| 2015-06-24 | ISSUE LOG
| 2015-06-25 | "MJSCO_pptaccountdashboard_new" script was prepared and standardized
| 2015-06-26 | "MJSCO_SF2" flow was rescripted and prepared and validated for Ptoduction Data. Scenario with all 6 scripts was prepared for the smoke test
| 2015-06-29 | Scenario for 6 Users was prepared as per workload matrix
| 2015-07-03 | Could not start the scripting for MJSCO phase 2, as the login URL is throwing Proxy Error.
| 2015-07-06 | MJSCO Portal down due to proxy issue
| 2015-07-07 | Script preparation for MJSCO Phase 2 execution.
| 2015-07-08 | Script preparation for MJSCO Phase 2 execution (Dividends).
Monitoring setup
| 2015-06-30 | Tried to connect the Web servers in Sitescope, though jump servers, as per Surendra's note
Execution Phase
| 2015-06-29 | One 6 User Load Test executed
| 2015-06-30 | Two tests with 6 and 12 User loads were executed
| 2015-07-01 | Prepared the scenario for 24 and 48 Users Load Test.
| 2015-07-01 | Scenario creation for Endurance Test and test execution.
Reporting Phase
| 2015-06-29 | Analysis for 6 User Test was done and review meeting with the Project Team was held
| 2015-06-30 | Analysis for 6 Users Test was done and review meeting with the Project Team was held
| 2015-07-01 | Prepard detailled level Reports for 24 and 48 Users Load Tests.
| 2015-07-07 | Workflow validation and script recording for "RSTS_MJSCO_DividendOptions".
| 2015-07-08 | Completed the "RSTS_MJSCO_DividendOptions" script.
| 2015-07-10 | Final Summary Report ceation
MJSCORound2
Phase | Date | Comments
Develop/Modify Performance Test Scripts
| 2015-07-13 | Workflow walkthrough for MJSCO Phase 2 scripting.
| 2015-07-14 | Transaction Mappping Document creation for all the workflows
| 2015-07-15 | Fund Transfer Script Completion.
| 2015-07-16 | LoanInitiationApproval Baseline Script preparation.
| 2015-07-17 | LoanInitiationApproval Script modification.
| 2015-07-20 | Scripting for MJSCO Phase2
| 2015-07-21 | Scripting for MJSCO Phase2
| 2015-07-22 | Scripting for MJSCO Phase2
| 2015-07-23 | Scripting for MJSCO Phase2
| 2015-07-24 | Scripting for MJSCO Phase2
| 2015-07-27 | Scripting for MJSCO Phase2
| 2015-07-28 | Scripting for MJSCO Phase2
| 2015-07-29 | Scripting for MJSCO Phase2
| 2015-07-30 | Scripting for MJSCO Phase2
| 2015-07-31 | Script Standardization for MJSCO Phase2
| 2015-08-03 | Script Standardization for MJSCO Phase2
| 2015-08-04 | Script Standardization for MJSCO Phase2
| 2015-08-05 | Script Standardization for MJSCO Phase2
| 2015-08-06 | Workflow navigation and identification for Loans
| 2015-08-07 | Workflow navigation and identification for Loans
| 2015-08-10 | Portals workflow identification for Post Login activities.
| 2015-08-11 | Old script validation for MJSCO Phase2
| 2015-08-12 | Old script validation for MJSCO Phase2
| 2015-08-13 | Portals flow identification and follow up with the project team for MJSCO
| 2015-08-14 | Scripting for Loan Repayment
| 2015-08-17 | Scripting for Loan Repayment
| 2015-08-18 | Scripting for Loan Repayment
| 2015-08-19 | Scripting for Loan Repayment
| 2015-08-20 | Scripting for Loan Repayment
| 2015-08-21 | Scripting for Loan Repayment
| 2015-08-24 | Scripting for Loan Repayment
| 2015-08-25 | Scripting for Loan Repayment
| 2015-08-26 | Scripting for Loan Repayment
| 2015-08-27 | Scripting for Loan Repayment
| 2015-08-28 | Reporting and Analysis for FMT migration (Test9)
| 2015-08-31 | Validated MJSCO Round1 scripts
| 2015-09-01 | MJSCO Phase1 script fix
| 2015-09-03 | MJSCO Phase1 script fix, 1 Reporting for Load Test
| 2015-09-04 | Monitoring Endurance Test for MJSCO
| 2015-09-07 | MJSCO Round 2 script validation and modification.
| 2015-09-08 | MJSCO Round 2 script validation and modification.
| 2015-09-09 | Final Analysis Summary PPT preparation for Round 2.
| 2015-09-10 | MJSCO Round 2 script validation and modification.
| 2015-09-11 | Portal transactions mapping identification of data dependency.
| 2015-09-14 | Identified functional issue with "Withdrawal".
| 2015-09-15 | MJSCO reports identification and documentation.
| 2015-09-16 | MJSCO Round 2 script validation and modification.
| 2015-09-17 | MJSCO business flow identification and mapping.
| 2015-09-18 | Portals workflow identification for Release 1 with Mash Up screens.
| 2015-09-24 | Portals data consolidation
| 2015-09-25 | FMT Report creation
| 2015-11-09 | Script development for new flows shared by Sujesh
2015-11-11
2015-11-12
2015-11-13
| 2015-11-16 | MJSCO script validation
2015-11-17
2015-11-18
| 2015-11-19 | MJSCO scripting
| 2015-11-20 | MJSCO scripting
| 2015-11-23 | MJSCO 1 script fix
| 2015-11-24 | MJSCO 1 smoke test and MJSCO 2 script modification
| 2015-11-25 | MJSCO 2 script modification
| 2015-11-26 | MJSCO 2 script modification
| 2015-11-27 | MJSCO 2 script modification
| 2015-11-30 | Phase 3 script validation
| 2016-01-14 | Phase 3 script validation
| 2016-01-15 | Phase 3 script validation
| 2016-02-15 | Advisor Scripting
| 2016-02-16 | Advisor Script merging
| 2016-02-17 | Sponsor scripting
| 2016-02-19 | Monitoring counter setup
| 2016-02-22 | MJSCO reports identification
| 2016-02-23 | MJSCO scripting
| 2016-02-24 | Smoke test with MJSCO and eForms
| 2016-02-25 | Sponsor scripting
2016-02-26
| 2016-02-29 | Sposnor scripting
| 2016-03-01 | Monitoring counter setup, DMOS ticket raised for MJSCO
| 2016-03-02 | Monitoring counter setup
| 2016-03-07 | Advisor script
| 2016-03-08 | PoC for advisor portal with Ajax true client
| 2016-03-09 | Ajax scripting of advisor portal
| 2016-03-10 | IDT Script validation
| 2016-03-11 | SID screnario identification
| 2016-03-14 | Issues Identified in portal
| 2016-03-15 | Sponsor scripting
| 2016-03-16 | Sponsor scripting
| 2016-03-17 | Sponsor script merging
| 2016-03-18 | Server config
| 2016-03-21 | Duplicate server deleted
| 2016-03-22 | Portal scenario identification
| 2016-03-23 | Portal script tweaking
| 2016-03-24 | Portal script tweaking
| 2016-03-25 | Data dependency mappind document prep
| 2016-03-28 | MJSCO scenario identification
| 2016-03-29 | MJSCO script building
| 2016-03-30 | MJSCO script building
| 2016-03-31 | MJSCO script building
| 2016-04-01 | Perf test monitor checking and scenario design
| 2016-04-04 | FMT Migration test result
| 2016-04-05 | FMT Migration test result
| 2016-04-06 | FMT Migration test result
| 2016-04-07 | FMT Migration test result
| 2016-04-08 | MJSCO Scripting
| 2016-04-11 | FMT Migration test result
| 2016-04-12 | FMT Migration test result
| 2016-04-15 | Validation Portal test IDs and folow up with help desk and other team
| 2016-04-18 | Advisor and Sponsor Scripting
| 2016-04-19 | Sponsor scripting
| 2016-04-20 | Advisor and Sponsor Scripting and server setup
| 2016-04-21 | Advisor and Sponsor Scripting
| 2016-04-22 | MJSCO Scripting
| 2016-04-26 | Advisor pre-login script creation
| 2016-04-27 | Sponsor DS script in Ajax
| 2016-04-28 | Participant pre-login script creation, portal script validation
| 2016-04-29 | Server config
Monitoring setup
Execution Phase
Reporting Phase
IDT MJSCO Reporting
Phase | Date | Comments
Develop/Modify Performance Test Scripts
| 2015-10-06 | Script preparation for IDT MJSCO reporting.
2015-10-07
2015-10-08
2015-10-09
| 2015-10-19 | FMT Reporting
| 2015-10-21 | Script preparation for IDT MJSCO reporting.
2015-10-22
| 2015-12-16 | Ticket raised for MJSCO access
Monitoring setup
Execution Phase
Reporting Phase
MJSCO
Phase | Date | Comments
Develop/Modify Performance Test Scripts
| 2015-12-02 | MJSCO script validation and modification
| 2015-12-03 | MJSCO script validation
| 2015-12-04 | MJSCO script modification
| 2015-12-14 | Scripting completed for batch deposite screen
| 2015-12-15 | 1 round of load test execution
| 2015-12-18 | New clean up flow identified and recorded
| 2015-12-21 | Clean up script Creation
| 2015-12-22 | Clean up script modification
| 2015-12-23 | Clean up script Creation
| 2015-12-24 | Clean up script modification
| 2016-01-04 | Clean up script creation
| 2016-01-05 | Clean up script modification
| 2016-01-06 | MJSCO Smoke test and result creation
Monitoring setup
Execution Phase
Reporting Phase
FMT
Phase | Date | Comments
Develop/Modify Performance Test Scripts
Monitoring setup
| 2015-12-02 | Server setup
Execution Phase
Reporting Phase
| 2015-12-01 | Reporting and analysis
| 2016-01-07 | Reporting and analysis
MJSCORound3
Phase | Date | Comments
Develop/Modify Performance Test Scripts
| 2015-11-30 | Phase 3 script validation
| 2015-12-03 | Phase 3 script validation
Portals
Phase | Date | Comments
Develop/Modify Performance Test Scripts
| 2015-12-17 | After receiving the credentials for Advisor, Participant, Sponsor and MJSCO Portals TTD creation started; Participant portal script recorded.
| 2015-12-30 | Portal Script creation
| 2015-12-31 | Portal Script Modification
| 2016-01-11 | Participant Portal Script Modification
| 2016-01-12 | Sponsor Portal Script Recording
| 2016-01-13 | Sponsor portal Script Modification
2016-01-18
| 2016-01-19 | MJSCO Phase 2 script creation
2016-01-20
| 2016-01-21 | MJSCO Phase 2 script creation
| 2016-01-22 | Portal script modifiction
| 2016-01-25 | Sponsor portalScript creation and MJSCO script modification
| 2016-01-27 | MJSCO script fixing in PP
| 2016-01-28 | MJSCO script fixing in PP
| 2016-01-29 | Sponsor portalScript creation and MJSCO script modification
| 2016-02-01 | Sponsor script modification
| 2016-02-02 | Advisor script creation
| 2016-02-03 | MJSCO script validation
| 2016-02-04 | MJSCO Script modification
| 2016-02-05 | MJSCO Script modification
| 2016-02-08 | Advisor Script Modification
| 2016-02-09 | Sponsor Script Modification
| 2016-02-10 | E-Form Script Creation
| 2016-02-11 | E-Form Script Modification
| 2016-02-12 | Advisor Script Modification
Monitoring setup
Execution Phase
Reporting Phase
Monitoring setup
Execution Phase
Reporting Phase

## Risks and issue
Risk

## temp
CUBE | Planned Start Date | Planned End Date
| 2015-10-01 | 2015-11-06
Design Phase: | 2015-10-01 | 2015-10-16
Architectural Overview | 2015-10-01 | 2015-10-16
Demo, Access and Setup by Project/QA Team | 2015-10-01 | 2015-10-16
Identify Inscope/out of Scope Transactions | 2015-10-01 | 2015-10-16
Identify the Performance Flows for Script Development/Documentation | 2015-10-01 | 2015-10-16
Design Test Scenarios | 2015-10-01 | 2015-10-16
Enviornment,Monitoring requirements (Pre-Prod/PROD) | 2015-10-01 | 2015-10-16
Performance Test Data Requirements | 2015-10-01 | 2015-10-16
Prepare, Publish, Review and Sign-OFF Performance Test Plan | 2015-10-01 | 2015-10-16
Build Phase | 2015-10-12 | 2015-10-23
Test Environment Delivery | 2015-10-12 | 2015-10-23
Data Preperation | 2015-10-12 | 2015-10-23
Develop/Modify Performance Test Scripts | 2015-10-12 | 2015-10-23
Monitoring setup | 2015-10-12 | 2015-10-23
LOAD MODEL | 2015-10-12 | 2015-10-23
Scenarios development and Review | 2015-10-12 | 2015-10-23
Execution Phase | 2015-10-26 | 2015-11-06
Profiled Performance Test Execution, Analysis, Remediation | 2015-10-26 | 2015-11-06
Stress Test Execution, Analysis, Remediation | 2015-10-26 | 2015-11-06
Duration Test Execution, Analysis, Remediation | 2015-10-26 | 2015-11-06
Reporting Phase | 11/62015 | 2015-11-06
Prepare Final Test Results | 11/62015 | 2015-11-06
Review the Test Results | 11/62015 | 2015-11-06